At first, our group have finished the project in time.

This is our project milestones. Although there are some difference between the fact and the plan. We succeed in completing the project in 25/12/2016.

About the Quality, As we mentioned last time. We have some problem in keeping the quality of QR code. After a lot of attempt in different format and QR code generator. We can ensure the quality of our product. All of information can be read correctly.

About the budget. Last time, we said that we are going to give two version of the product. Because the electronic version needs much less budget. And the quantity of paper version has been decreased. So, half of the budget has been saved.

About the measurement of our project.

This is the investigation of our project reader, the quantity of specimen is 15.

Most of criteria we set in the scope statement has been reached.

Including :

More than 95% of the information is correct.

More than 70% of the reader consider the content of guide is interesting.

More than 50% of the experienced tourists consider the information is useful.

But

More than 25% of the reader have willing to have a tourist according to the guidance.

We did not reach this criteria.

May be the reason is that some part of our product is not good enough, such as tear section. We did not persuade the travel agency to give us special discount. Which caused our tourism guide not motivating enough.